## Example1 (hidden)
Initiative 3(a): Repair and maintain wells and farm ponds
Start Date: 01/08/2014
End Date: 15/03/2016
First level # | Second level # | Third level # | First level | Second level | Third level | No | Milestone | No | Detailed activity | Responsibility | Planned start date (dd.mm.yyyy) | Planned end date (dd.mm.yyyy) | Length (in weeks)
1 |  |  | 1 | 1. | 1.. | 1 | Create subsidy policy on O&M of wells and farm ponds |  |  | RDD, Water Conservation Dept, Agri Dept, GSDA | 2014-08-01 | 2014-11-05 | 12
1 |  |  | 1 | 1. | 1.. |  |  | 1.1 | Issue a circular for formation of technical committee at state level for policy formulation | Secretary RDD and Water Conservation, Secretary Agri. Dept. & GSDA | 2014-08-01 | 2014-08-31 | 4
[8 empty] | 1.2 | Draft policy based on policy for O&M of drinking water wells and define criteria for selection of beneficiaries (includes obtaining feedback from other department, resource persons and public on draft policy) and draft amendment to NREGA policy to allow use of machinery for maintenance of wells | Technical committee | 2014-09-01 | 2014-10-31 | 8
1 |  |  | 1 | 1. | 1.. |  |  | 1.3 | Discuss in Cabinet meeting and obtain Cabinet's approval | Minister of Water conservation & WSSD | 2014-11-05 | 2014-11-05 | 0.1
[8 empty] | 1.4 | Discuss in GOI Cabinet meeting on amendment of NREGA to allow use of machinery for maintenance of wells | Minister of Water conservation, RDD | 2014-11-12 | 2014-11-12 | 0.1
[8 empty] | 1.5 | Issue Government Resolution | Water Conservation, RDD & WSSD | 2014-11-13 | 2014-11-15 | 0.42857
1 |  |  | 1 | 1. | 1.. | 2 | Conduct survey of maintainance level of wells and farm ponds |  |  | Irrigation Dept, Talathi, Gramsewak, Krishisewak, GSDA | 2014-11-15 | 2015-03-31 | 19
[8 empty] | 2.1 | Draft concept for ideal well and farm ponds (i.e. performance standards of wells and farm ponds) based on census of MI Schemes by GOI (Minister of Water Resources) | Irrigation Dept. (Local Sector) assisted by Talathi, Gramsewak, Krishisewak, & GSDA) | 2014-11-15 | 2014-11-30 | 2
[8 empty] | 2.2 | Assign areas to state irrigation dept. officers to conduct survey/census | Irrigation (local sector division) | 2014-12-01 | 2014-12-07 | 1 | Repeated every 5 years
1 |  |  | 1 | 1. | 1.. |  |  | 2.3 | Conduct survey/census based on set performance standards | Irrigation Dept. (Local Sector) assisted by Talathi, Gramsewak, Krishisewak, & GSDA) | 2014-12-08 | 2015-03-31 | 16 | Repeated every 5 years
1 |  |  | 1 | 1. | 1.. | 3 | Determining financial source |  |  | RDD, Water Conservation Dept, Agri Dept | 2014-12-01 | 2015-04-15 | 6
1 |  |  | 1 | 1. | 1.. |  |  | 3.1 | Table into annual state budget process at supplementary budget session | RDD, Water Conservation Dept, Agri Dept | 2014-12-01 | 2014-12-15 | 2 | 2014 only
[8 empty] | 3.2 | Decide financial source (whether MGNAREGA, IWMP, SCP/TSP Schemes at DPC) at state budget session | RDD, Water Conservation Dept, Agri Dept | 2015-03-15 | 2015-04-15 | 4 | 2015 onwards
1 |  |  | 1 | 1. | 1.. | 4 | Awareness Programme |  |  | Master trainers, Block Development Officer (BDO) | 2015-04-01 | 2015-09-09 | 21
1 |  |  | 1 | 1. | 1.. |  |  | 4.1 | Prepare training and awareness module (how to maintain, what subsidy can be obtained) to be used via Initiative 10 | Master trainers at block level | 2015-04-01 | 2015-04-07 | 1
[8 empty] | 4.2 | Awareness to farmers on new policy/ scheme/ benefits at block level | Master trainers | 2015-04-08 | 2015-05-08 | 4 | Annual
[8 empty] | 4.3 | Farmers choose either option 1 (subsidy) or option 2 (NREGA/schemes): | Block development officer | 2015-05-09 | 2015-07-09 | 8 | Annual
[8 empty] | 4.4 | Option 1 - Application for subsidy scrutiny and finalisation of bebeficary Option 2 - Farmers have to work under NREGA/ hire NREGA
[8 empty] | 4.5 | Training farmers and labourers on how to maintain - use initative 10 | Master trainers | 2015-07-09 | 2015-09-09 | 8 | Annual

## Intiative 1
Company:
Start Date:
End Date:
First level # | Second level # | Third level # | First level | Second level | Third level | No | Milestone | No | Detailed activity | Responsibility | Planned start date (dd.mm.yyyy) | Planned end date (dd.mm.yyyy) | Length (in weeks)
1 |  |  | 1 | 1. | 1.. | 1
1 |  |  | 1 | 1. | 1.. |  |  | 1.1
1.2
1.3
1 |  |  | 1 | 1. | 1.. |  |  | 1.4
1 |  |  | 1 | 1. | 1.. |  |  | 1.5
1.6
1.7
1.8
1.9
1.1
1 |  |  | 1 | 1. | 1.. | 2
1 |  |  | 1 | 1. | 1.. |  |  | 2.1
2.2
1 |  |  | 1 | 1. | 1.. |  |  | 2.3
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 3
1 |  |  | 1 | 1. | 1.. |  |  | 3.1
1 |  |  | 1 | 1. | 1.. |  |  | 3.2
1 |  |  | 1 | 1. | 1.. |  |  | 3.4
1 |  |  | 1 | 1. | 1.. | 4
1 |  |  | 1 | 1. | 1.. |  |  | 4.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 5
1 |  |  | 1 | 1. | 1.. |  |  | 5.1
5.2
5.3
1 |  |  | 1 | 1. | 1.. |  |  | 5.4
1 |  |  | 1 | 1. | 1.. |  |  | 5.5
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 6
1 |  |  | 1 | 1. | 1.. |  |  | 6.1
1 |  |  | 1 | 1. | 1.. | 7
1 |  |  | 1 | 1. | 1.. |  |  | 7.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 8
1 |  |  | 1 | 1. | 1.. |  |  | 8.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 9
1 |  |  | 1 | 1. | 1.. |  |  | 9.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 10
1 |  |  | 1 | 1. | 1.. |  |  | 10.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 11
11.1
1 |  |  | 1 | 1. | 1.. | 12
12.1
1 |  |  | 1 | 1. | 1.. |  |  | 12.2
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 13
1 |  |  | 1 | 1. | 1.. |  |  | 13.1
1 |  |  | 1 | 1. | 1.. | 14
1 |  |  | 1 | 1. | 1.. |  |  | 14.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 15
1 |  |  | 1 | 1. | 1.. |  |  | 15.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1.. | 16
1 |  |  | 1 | 1. | 1.. |  |  | 16.1
1 |  |  | 1 | 1. | 1..
1 |  |  | 1 | 1. | 1..
17
17.1
18
18.1
18.2
18.3
19
19.1
20
20.1
20.2
21
21.1
22
22.1